## liveDownload Roadmap
ID | Priority | Status | Area | Title | Description | Source | Created On | Owner | Link
RM-013 | P1 | Open | Live | Twitch Token Expiry Recovery (S3-04) | Twitch auth tokens expire mid-recording. Recovery mode should detect the 401/403 response, signal token expiry, and re-acquire token without losing the recording session. | Sprint-4 | 2026-03-13 | Gman
RM-014 | P1 | Open | Testing | VOD Testing — Twitch (AES-128 + fMP4) | End-to-end VOD download validation on Twitch. Covers AES-128-CBC decryption path and fMP4 init-segment handling in VodDownloader. | Roadmap | 2026-03-13 | Gman
RM-015 | P1 | Open | Testing | VOD Testing — SOOP | End-to-end VOD download validation on SOOP (sooplive.co.kr). Validate segment fetching, filename macro extraction, and file output. | Roadmap | 2026-03-13 | Gman
RM-016 | P1 | Done | Testing | RDP Headless Server — Full Regression | Full regression test on RDP-managed remote server after v0.7.29.x changes. Confirm icon responsiveness, bounds fallback, polling, and auto-record all function correctly. | Roadmap | 2026-03-13 | Gman
RM-017 | P2 | Done | Docs | README Documentation | Write full README covering: installation, all settings, WRU editor actions, filename macros, live vs VOD flows, recovery mode, RDP deployment notes, and ffmpeg post-processing. | Roadmap | 2026-03-13 | Gman
RM-018 | P2 | Open | Deploy | Chrome Web Store Submission | Prepare store listing: description, screenshots, privacy policy, permissions justification. Submit for review. Ensure manifest and icon meet store requirements. | Roadmap | 2026-03-13 | Gman
RM-019 | P2 | Done | Core | Timestamps from UTC to Local Time | Filename timestamps seem be in UTC. We need to change it to local time. | Roadmap | 2026-03-27 | Gman
RM-020 | P2 | Done | UI | Replace the Empty Stream Window | Look and feel is different from rest of our windows. Replace the middle portion with our branding, dither our icon as background to create brand awareness. For the Wait For Recording button, update style - similar to Stop Recording, instead of [] use hourglass and use a different pleasing color instead of Red. | Roadmap | 2026-03-27 | Gman
RM-021 | P2 | Done | Core | Check all models - use same style | Some modals say "liveDownloader says" | Roadmap | 2026-03-27 | Gman
RM-022 | P2 | Done | Core | Window title not updating after async translation | Window title not updating after async translation in VOD/single mode — file saves correctly but the tab title stays untranslated | Roadmap | 2026-03-27 | Gman
RM-023 | P2 | Open | Core | VOD title resolving as "Unknown" | VOD title resolving as "Unknown" — separate macro block needed for VOD vs live | Roadmap | 2026-03-27 | Gman
RM-024 | P3 | Open | Core | Threads Don't seem to go past 3, even when 5 set | Even when settings says 5 threads, max always seems to be three | Roadmap | 2026-03-28 | Gman
RM-025 | P2 | Done | Core | Batch Download Completion Issue | (1) Displays Download Complete, when just one is done (2) Seems to have trouble closing out the last download (3) Download in general needs to check if there is an active download in progress and prompt user to confirm Quit midstream | Roadmap | 2026-03-28 | Gman
RM-026 | P3 | Open | Live | Continuous Replay Recording | When a SOOP broadcast ends, the platform publishes the session as a sequential replay manifest. HLSEngine architecture supports this — implement automatic detection and recording of post-broadcast replays as a continuation of the live session. | Sprint-4 | 2026-03-28 | Gman
RM-027 | P3 | Done | Core | Graceful WASM Load Failure | If window.__ldWasm is not available when recording starts, stop cleanly with a user-facing error message instead of hanging in the recording state machine. Only triggered by a bad package — low priority. | Sprint-4 | 2026-04-02 | Gman
RM-028 | P3 | Done | UI | Application Font Review | Current font stack (system sans-serif) renders some text as smudged on Windows. Review and standardise font across modern-ui.css and index.css for crisp rendering across all UI components. | Roadmap | 2026-04-02 | Gman
RM-029 | P0 | Done | Core | IndexedDB cleanup uses wrong property name | worker.js:334 uses db.Name (capital N) instead of db.name. IDBDatabaseInfo property is lowercase. Silently fails on every startup, stale databases never cleaned up. | Code Review | 2026-04-13 | Gman
RM-030 | P0 | Done | Core | IndexedDB startup cleanup conflicts with directory handle storage | worker.js deletes all IndexedDB databases on startup, but settings.js stores the root directory handle in IndexedDB ('liveDownload' database). If RM-029 is fixed without excluding the liveDownload DB, auto-record directory handles will be destroyed on every browser restart. Fix both together: correct the property name AND add exclusion for 'liveDownload' DB. | Code Review By Opus | 2026-04-13 | Gman
RM-031 | P0 | Done | WASM | WASM loader race condition — module defers after classic scripts | index.html loads wasm/loader.js as <script type="module"> (deferred) but live-integration.js as classic <script> (immediate). WASM may not be ready when first segment downloads. downloadSegment() throws hard error 'WASM module not loaded'. Add readiness gate: Promise in loader.js that start() awaits before first download. | Code Review By Opus | 2026-04-13 | Gman
RM-032 | P0 | Done | Live | SOOP autoplay check dead — .co.kr already rewritten to .com | ui/autorecord.js:27 checks href.includes('sooplive.co.kr') but polling-manager.js:364 already rewrites URLs from .co.kr to .com before opening the auto-record window. The autoplay injection in autorecord.js never fires for WRU-triggered recordings. Fix: check for 'sooplive.com' or 'sooplive' (without TLD). | Code Review By Opus | 2026-04-13 | Gman
RM-033 | P1 | Done | Live | Recovery fileIncrement never incremented — completion shows wrong count | live-integration.js: fileIncrement is initialized to 0 and read in showCompletionScreen() but never incremented in resumeRecording(). Completion screen always shows '1 file total' even after multiple recovery files. | Code Review By Opus | 2026-04-13 | Gman
RM-034 | P1 | Done | Core | VERSION constant stale — shows 0.7.30.08 vs manifest 0.7.40.00 | live-integration.js line 7: const VERSION = '0.7.30.08' while manifest.json says 0.7.40.00. Console logs and any version-dependent logic uses wrong version. Sync to manifest or read dynamically. | Code Review By Opus | 2026-04-13 | Gman
RM-035 | P1 | Done | Core | Settings panel hardcodes default-format to TS, ignoring MKV preference | settings.js:283 and :395 always set default-format to 'ts', overriding user's MKV selection from the original dropdown. Users who prefer MKV containers cannot use that preference for live recordings. | Code Review By Opus | 2026-04-13 | Gman
RM-036 | P1 | Done | UI | isLiveStream HTTP fetch fires on every table re-render | ui/stream-table.js:25-33 calls LiveMonitor.isLiveStream() for every m3u8 on every renderStreamsTable() call. Each check does 1-2 HTTP fetches. Triggered on every new stream detected and filter toggle. Cache isLive on first evaluation in extractAndStoreEntry(). | Code Review By Opus | 2026-04-13 | Gman
RM-037 | P1 | Done | Core | addWRUCurrentTab returns undefined waitInfo fields | wru-manager.js:117 returns waitResult.nextCheck and .checkInterval but startWaiting() only returns {success:true} — fields are always undefined. Notification shows fallback '15 minutes' but data contract is broken. | Code Review By Opus | 2026-04-13 | Gman
RM-038 | P2 | Open | WASM | SegmentResult.bytes() triple-copies segment data | lib.rs:32 — bytes() calls .clone() on Vec<u8>, creating a full copy in WASM linear memory before wasm-bindgen copies again to JS Uint8Array. For 4hr stream at 6Mbps this is ~10GB unnecessary allocations. Use std::mem::take() or restructure so bytes bypass WASM. | Code Review By Opus | 2026-04-13 | Gman
RM-039 | P2 | Open | Live | pendingSegments array grows without bound | live-integration.js: pendingSegments has no size cap. If manifest polling adds segments faster than download (high bitrate, slow network), array grows indefinitely. Add cap with oldest-segment eviction since stale segments are likely expired from CDN. [Partially mitigated by RM-062 try/finally fix — write loop no longer deadlocks, but array still has no hard cap] | Code Review By Opus | 2026-04-13 | Gman
RM-040 | P2 | Open | Live | BoundedSet stores every URL twice (Set + Array) | live-integration.js:81-96 — BoundedSet maintains both a Set and an Array queue. For 2000 HLS segment URLs (~200 chars each), ~800KB redundant. Use Set iteration order (insertion-order per spec) to eliminate the array. | Code Review By Opus | 2026-04-13 | Gman
RM-041 | P2 | Open | UI | Status polling wakes service worker every 30s with 12+ API calls | ui/status-bar.js fires updateHeaderStatusCounts() every 30s via setInterval, sending 2 runtime messages. Each triggers chrome.tabs.get() per waiting tab. With 10 WRU entries = 12 API calls every 30s, waking SW from sleep. Reduce to 60s or poll only when focused. | Code Review By Opus | 2026-04-13 | Gman
RM-042 | P3 | Done | Live | _loadSettings and reloadSettings are copy-pasted — will diverge | live-integration.js lines 585-623: identical logic with identical storage keys. Adding a new setting to one and forgetting the other causes silent divergence. Extract single _applySettings(storageResult) helper called from both. | Code Review By Opus | 2026-04-13 | Gman
RM-043 | P3 | Done | Core | Autoplay injection logic duplicated in 3 separate files | Three independent implementations of 'click the play button': polling-manager.js _injectAutoplay(), live-integration.js _injectTabAutoplay(), and ui/autorecord.js checkAutoRecord(). Each has different strategy order and fireClick implementations. Extract into shared content script. | Code Review By Opus | 2026-04-13 | Gman
RM-044 | P3 | Open | Core | self.storage global name collision risk in content pages | worker.js:152 injects self.storage = new Map() into every tab's content context via chrome.scripting.executeScript. 'storage' is a common name that could collide with page scripts. Rename to __liveDownload_streams or similar. | Code Review By Opus | 2026-04-13 | Gman
RM-045 | P3 | Done | Core | Placeholder homepage_url in manifest.json | manifest.json:24 — homepage_url is 'https://github.com/your-repo/liveDownload'. Chrome Web Store reviews flag placeholder URLs. Update before submission (see RM-018). | Code Review By Opus | 2026-04-13 | Gman
RM-046 | P3 | Done | Core | showNotification() duplicated in ui/utils.js and live-integration.js | Two independent implementations with different auto-dismiss timing (8s vs 5s) and animation (one has CSS animation, one doesn't). Extract into shared utility used by both. | Code Review By Opus | 2026-04-13 | Gman
RM-047 | P3 | Done | UI | Dead code: modern-ui.js is 2,064 lines never loaded | modern-ui.js has been replaced by the ui/ directory modules but the file still ships in the extension package. It's never loaded in index.html (only modern-ui.css is). Remove from package to reduce size and avoid confusion. | Code Review By Opus | 2026-04-13 | Gman
RM-048 | P3 | Open | UI | ~50 global functions with no namespace from ui/ modules | All ui/ functions (setupWRUEditor, loadWRUList, renderStreamsTable, etc.) are bare globals on window. Name collisions possible if plugin system grows. Consider wrapping in namespace object (window.LD = {}). | Code Review By Opus | 2026-04-13 | Gman
RM-049 | P4 | Open | Live | handlingStreamDetected Set never cleaned on success path | polling-manager.js: handlingStreamDetected.delete(tabId) only fires on 'streams disappeared' and error branches. Successful auto-record leaves entry forever. If Chrome reuses tab ID, fresh monitoring attempt is blocked. | Code Review By Opus | 2026-04-13 | Gman
RM-050 | P4 | Open | Live | stop() can block UI for up to 30 seconds with no hard abort | live-integration.js stop(): while loop waits for checkInFlight/downloadInFlight up to 30s. If WASM or fetch genuinely hangs, 30-second UI freeze. Consider hard AbortController mechanism. | Code Review By Opus | 2026-04-13 | Gman
RM-051 | P4 | Open | Core | VodDownloader._fetchWithRetry can recurse infinitely | vod-downloader.js:191 — when onError callback provides replacement URL, _fetchWithRetry calls itself recursively. If user keeps retrying same bad URL, unbounded recursion. Add recursion counter or override limit. | Code Review By Opus | 2026-04-13 | Gman
RM-052 | P4 | Open | Live | externallyAbortedTabs Set leaks entries | polling-manager.js: entries added in handleWRUTabClosed and deactivateWRU but only cleaned in stopWaiting(). Race conditions leave stale entries. Tab ID reuse could cause spurious aborts. | Code Review By Opus | 2026-04-13 | Gman
RM-053 | P4 | Open | UI | Batch download timeout timers never cleared on success | ui/stream-table.js:405 — 5-minute setTimeout in downloadSingleStream never cleared when download completes. During batch of 10 files, 10 lingering timers hold closures for 5 minutes each. | Code Review By Opus | 2026-04-13 | Gman
RM-054 | P1 | Done | Core | Unified download pipeline | Auto-record routes through form#hrefs submit → parse() → download() → LiveMonitor instead of constructing LiveMonitor directly. One construction point. Uses self.aFile proxy with _autoRecord flag. | Code Review | 2026-04-14 | Gman
RM-055 | P2 | Done | Core | Unified window creation | All chrome.windows.create calls consolidated into _createWindowWithFallback() in window-manager.js. 3-level fallback chain. 10 scattered calls → 3 in one function. | Code Review | 2026-04-14 | Gman
RM-056 | P2 | Done | Core | Unified autoplay injection | Created autoplay.js — single source of truth. Replaces 3 divergent implementations. Platform-agnostic 5-strategy cascade. | Code Review | 2026-04-14 | Gman
RM-057 | P2 | Done | Live | Checkpoint system for crash protection | Periodic file checkpointing with toggle + configurable interval (5-120 min). Auto-record always checkpoints (10 min default). Service worker notification on window crash. | Code Review | 2026-04-14 | Gman
RM-058 | P1 | Done | Core | Auto-save to configured root directory | Submit handler tries configured root directory first with queryPermission check. Falls back to showSaveFilePicker only when no directory configured or permission lost. Eliminates save dialog for both VOD and live manual downloads. | Testing | 2026-04-14 | Gman
RM-059 | P1 | Done | Live | OPFS fallback for auto-record without directory | Auto-record without configured directory now falls back to OPFS instead of trying showDirectoryPicker() which requires user gesture and silently fails. | Testing | 2026-04-14 | Gman
RM-060 | P0 | Done | Core | Translation called N times per page (N=stream count) | build.js called translateText() inside per-entry name() function. Fixed: translate page title once before entry loop, cache result. 252 API calls → 1. | Log Analysis | 2026-04-14 | Gman
RM-061 | P0 | Done | Core | isLiveStream() called per stream entry | stream-table.js checked isLiveStream() for every m3u8 in streamData. Fixed: check one representative stream, apply result to all. 252 manifest fetches → 1. | Log Analysis | 2026-04-14 | Gman
RM-062 | P0 | Done | Live | Write loop crash causes permanent deadlock | If outputWritable.write() threw, downloadInFlight stayed true forever. processQueue() returned immediately on every call. Pending segments grew unbounded (768+). Checkpoint saved 0 MB. Fixed: try/finally in processQueue() + safety reset in runLoop() catch. | Log Analysis | 2026-04-14 | Gman
RM-063 | P1 | Done | Live | Recovery timeout shows beforeunload dialog | Recovery timeout bypassed stop() and called chrome.windows.remove() directly with beforeunload handler still active. Fixed: call stop() which removes handler, finalizes file, then auto-closes. | Log Analysis | 2026-04-14 | Gman
RM-064 | P1 | Done | Live | Auto-record windows don't auto-close after recording ends | checkReenterWaiting() only auto-closed if autoclose setting was on. Auto-record windows now always auto-close regardless of that setting. | Log Analysis | 2026-04-14 | Gman